## Budget Overview
| Activity | Amount
Expenses
| Phase 1: Campaign Kick Off | 19260
| Phase 2: ID & Persuasion | 65821.44
| Phase 3: GOTV | 23725.99
| TOTAL EXPENSES | 108807.43
Income
| Budget | 90000
| TOTAL REVENUE | 90000
Total Funding
| Total Income | 90000
| Total Expenses | 108807.43
| Total Surplus or Shortage | -18807.43

## Budget
SAMPLE BELOW
|  | Phase1: Campaign Kick-off |  |  | Phase 2: ID & Persuasion |  |  |  | Phase 3: GOTV
|  | June | July | Phase 1 Total | August | September | October | Phase 2 Total | November | Phase 3 Total
Events
| Campaign Kick Off Party | 1000 |  | 1000 |  |  |  | 0 |  | 0
| Election Day materials |  |  | 0 |  |  |  | 0 | 89.47 | 89.47
Field
| Campaign postcards | 1200 |  | 1200 |  | 1187.67 | 782 | 1969.67 |  | 0
| Campaign yard signs |  |  | 0 |  | 2605 | 1356 | 3961 | 1926 | 1926
| Campaign mailer 1 |  |  | 0 |  |  | 14508 | 14508 |  | 0
| Campaign mailer 2 |  |  | 0 |  |  | 14508 | 14508 |  | 0
| Campaign mailer 3 |  |  | 0 |  |  |  | 0 | 14508 | 14508
Comms/Media
| Digital (FB ads) | 100 | 100 | 200 | 200 | 100 | 100 | 200 | 100 | 100
| Radio Ads |  |  | 0 |  |  | 4584 | 4584 |  | 0
| WFRE/WFMD |  |  | 0 |  |  |  | 0 | 2444.25 | 2444.25
Tools | [7 empty] | 0
| LAN & miniVAN |  |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  | 0
Total |  | 2300 | 100 | 2400 |  | 3892.67 | 35838 | 39730.67 | 19067.72 | 19067.72
[5 empty] | TOTAL: PHASES 1-3 | 61198.39
***Please note: a good budget has projected expenses and then is updated to include actual costs.
Field Estimate
| 6 weeks until Nov 6th |  | 4 FT Canvassers
| 15,469 phones | phones | 14,791 doors | doors
| 2578 | per week | 2465 | per week
| 644.5 | person per week | 616.25 | person per week
| 30 | per hour | 30 | per hour
| 42 hours x $15 | 630 | 4 | 2520 | person week
|  |  |  | 6 | weeks total
|  |  |  | 15120 | total
Note on H9: 200
Note on J9: 300 small signs

## Calendar
2026 | NOVEMBER |  | SUNDAY
CALENDAR YEAR | CALENDAR MONTH |  | FIRST DAY OF WEEK
46327 | 44865 | 44866 | 44867 | 44868 | 44869 | 44870
2026-11-01 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05
GOTV | GOTV | Race 1 canvassers deploy, led by SPTA Trainer John Smith; Digital ads for Race 1, 2, 4, 6 | GOTV 5-7pm | GOTV 5-7pm | GOTV 5-7pm | GOTV 12-4pm
2026-11-08 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12
GOTV 12-4pm | GOTV Sign crew 5-8pm | Election Day | Campaign signs need to be removed by 2pm
2026-11-15 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19
Campaign finance report due
2026-11-22 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26
2026-11-29 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03
2026-12-06 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10

## Canvass
Precinct | 18-64 | Turf | People | Doors | Canvasser | Date | 65-100 | Turf | People | Doors | Canvasser | Done | Notes
26-002
| 27313319-15402 | 1 | 76 | 58 | Frank Malta | 2018-10-17 | 27313133-86951 | 1 | 77 | 61 | Drue Jones | 2018-10-20
| 27313320-90459 | 2 | 58 | 36 | Frank Malta | 2018-10-22 | 27313134-28242 | 2 | 93 | 68 | Matt Stansbury | 2018-11-01
| 27313321-24059 | 3 | 103 | 71 | Kerrie Malta | 2018-11-04 | 27313135-90204 | 3 | 61 | 50 | Mike Herrod | 2018-11-01

## Election Day
Precinct | Votes | Location | Address | City | Zip | 6:30am-1pm | 1pm-8pm | Notes
18-001 | 2146 | Twin Ridge Elementary School | 1106 Leafy Hollow Circle | Mount Airy | 21771 | Richie Baer Stephen Ward | Richie Baer Stephen Ward | Wives will join too